## Slide 1
Delivery Infrastructure Overview
For CEO Approval
Version 1.0 | January 2026 | Dom
Full Spec: github.com/synapticera/helm-miner/docs/specs/SPEC-DELIVERY-INFRASTRUCTURE.md

## Slide 2
Executive Summary
Solution: 8-Stage AI-Integrated Pipeline
8-Stage Delivery Pipeline
Intake > Spec > Task > Implement > Validate > Staging > Release > Monitor
Clear Ownership
Every stage has defined owner and responsibilities
Defined Outputs
Each stage produces specific deliverables before proceeding
AI-Powered Throughout
Claude assists at every stage: drafting, coding, reviewing, deploying
Constraints
Platform
GCP Cloud Run (agent-finder + staging)
CI/CD
GitHub Actions for automated workflows
Project Management
Jira (MIN project for all tickets)
AI Task Tracking
Backlog MCP (Claude-integrated)
Budget
Minimize new tooling costs - use existing infra + free tiers

## Slide 3
TL;DR: What Bill Needs to Approve
KEY DECISIONS
Dom's Authority
Full control over HOW things get built
Team management & assignments
Delivery process & execution
Technical decisions
Sprint planning & tracking
Code review & deployment
Bill's Authority
Strategic control over WHAT gets built
Product direction & vision
Backlog prioritization
Feature decisions
Override on priorities
Product Planning (Mon/Wed)
Dom's Process
The system being approved
8-stage delivery pipeline
x-protocol cc development
1-week sprint cadence
5 core principles
5-day initial implementation (Jan 27-31)
Go-live Friday Jan 31
Open Question: Who owns QA? (Manual testing before production - needs to be assigned)

## Slide 4
Team Structure & Roles
Dom / Charles
Owner: Stages 2-8
Writes specs
Creates tasks
Reviews PRs
Deploys to prod
Unblocks team
Does implementation too
Bill (CEO)
Owner: Stage 1 (Intake)
Product direction
Backlog priority
Feature decisions
Product Planning
Offshore Devs
Owner: Stage 4
Implements tasks
Writes tests
Creates PRs
Works with AI
QA (TBD)
Owner: Stage 5
Manual testing
User acceptance
Bug verification
Sign-off

## Slide 5
5-Day Delivery Infrastructure Implementation Timeline
1
Mon Jan 27
Foundations
Create Jira Epic
Create develop branch
Pre-commit hook (MIN-XX)
PR template
Update CLAUDE.md
Document DoR/DoD
Complete documentation
2
Tue Jan 28
Automation
Add linting
Setup automated tests
GitHub Actions CI
Branch protection
Test CI with PR
3
Wed Jan 29
Deployment
Create staging service
Auto-deploy workflow
Prod deploy workflow
Test deployments
Create runbook templates
4
Thu Jan 30
Team Prep
Create Backlog tasks
Spec template
Fill deploy runbook
Onboarding doc
Buffer for fixes
5
Fri Jan 31
GO LIVE
Final system check
Team training
Sprint Planning
Assign tickets
SYSTEM LIVE
Start: Monday Jan 27, 2026
Go-Live: Friday Jan 31, 2026
Sprint 1: Monday Feb 3, 2026

## Slide 6
Core Principles
1
Sprint Commitment is Sacred
NO changes mid-sprint. New requests go to backlog. Emergencies (P0) are the ONLY exception.
2
We Move 50x Faster with AI
AI is not optional - it's how we work. Every stage uses Claude. ”PROCESS" not "prompt and pray."
3
Build AI-Native Product Features
Conversational > Traditional BI. Don't build dashboards when AI can answer questions.
4
Security Shall Not Block
Move fast. SOC 2 when enterprise customers demand it. Build securely, but don't wait for perfect.
5
Continuously Innovate Delivery
Retro action items are P0. Improve delivery weekly. Automate anything done 3+ times.
These principles override process when in conflict. Example: Security review would delay sprint? Skip it, document the risk, move forward.

## Slide 7
AI Integration - Claude at Every Stage
1
INTAKE
Draft Jira stories from meeting transcripts
Suggest acceptance criteria
Clarify requirements
2
SPEC
Generate technical specs
Explore codebase patterns
Identify files to modify
3
TASK
Decompose specs into tasks
Identify dependencies
Estimate effort
4
IMPLEMENT
Write tests first (TDD)
Implement code
Format commits properly
5
VALIDATE
Create PRs with template
Fix review feedback
Run lint/format checks
6
STAGING
Monitor deployment
Check health endpoint
Report status
7
RELEASE
Create release PR
Create git tags
Update Jira to Done
8
MONITOR
Check logs for errors
Diagnose issues
Initiate rollback
PROCESS

## Slide 8
Solution Overview - 8-Stage Pipeline
1
INTAKE
Bill/Dom
→
2
SPEC
Dom/Charles
→
3
TASK
Dom/Charles
→
4
IMPLEMENT
Implementer
→
5
VALIDATE
Dom/Charles
→
6
STAGING
Auto
→
7
RELEASE
Dom
→
8
MONITOR
All
Pipeline Philosophy
Every feature flows through all 8 stages
No skipping stages (except P0 emergencies)
Clear ownership at each stage
AI (Claude) assists at every stage
Automated gates where possible
Sprint Flow
1-week sprints (Mon-Fri)
Sprint Planning: Friday 2 PM
Work assigned before weekend
Offshore starts Monday AM
Daily standups / sprint meetings
Quality Gates
Spec approval before task creation
Tests required before PR
PR review before merge
Staging verification before prod
Health check after deploy
Key: Stages 1-3 (Planning) happen before sprint. Stages 4-8 (Execution) happen during sprint.

## Slide 9
Stage 1: INTAKE
OWNER: Bill/Dom/Charles
Requirements gathering from stakeholders. All work starts here.
Key Points
Every request documented in Jira
No verbal-only requests
Acceptance criteria required
Priority assigned (P0-P3)
Product planning sessions (Mon/Wed)
🤖 AI Tasks (Claude)
Draft Jira story from conversation
Suggest acceptance criteria
Identify questions to clarify
Flag dependencies
Estimate complexity
Output: Jira ticket with acceptance criteria, ready for spec

## Slide 10
Stage 2: SPEC
OWNER: Dom / Charles
Technical specification creation. Defines HOW to build the feature.
Key Points
Written before ANY code
Includes file changes needed
Identifies testing approach
Documents edge cases
Reviewed before task creation
🤖 AI Tasks (Claude)
Generate technical spec from Jira
Explore codebase for patterns
Identify files to modify
Suggest test cases
Flag technical risks
Output: Technical spec document approved by Dom

## Slide 11
Stage 3: TASK
OWNER: Dom / Charles
Break spec into implementable tasks. Creates the sprint work.
Key Points
Each task is 2-4 hours max
Clear definition of done
Dependencies identified
Assigned to developer
Added to Backlog MCP
🤖 AI Tasks (Claude)
Decompose spec into tasks
Suggest task ordering
Identify dependencies
Estimate effort
Create Backlog tasks
Output: Tasks in Backlog, assigned and ready for sprint

## Slide 12
Stage 4: IMPLEMENT
OWNER: Developer
Actual coding work. AI-assisted development.
Key Points
Follow TDD (test first)
Use AI for coding
Follow code patterns
Small, focused commits
Update task status
🤖 AI Tasks (Claude)
Write failing test first
Implement code to pass test
Format code properly
Create descriptive commits
Check for edge cases
Output: Working code with tests, committed to feature branch

## Slide 13
Stage 5: VALIDATE
OWNER: Dom + QA
Code review and testing. Ensures quality before merge.
Key Points
PR created with template
CI must pass
Code review required
Manual QA testing
Acceptance criteria verified
🤖 AI Tasks (Claude)
Create PR with proper template
Fix linting issues
Address review feedback
Run test coverage check
Update documentation
Output: Approved PR ready to merge

## Slide 14
Stage 6: STAGING
OWNER: QA
Automatic deployment to staging environment.
Key Points
Auto-deploy on merge to develop
Health check verification
Staging URL for testing
Smoke test required
Stakeholder preview
🤖 AI Tasks (Claude)
Monitor deployment status
Check health endpoint
Report any failures
Verify key functionality
Alert on errors
Output: Feature live on staging, verified working

## Slide 15
Stage 7: RELEASE
OWNER: Dom
Production deployment. Manual trigger with verification.
Key Points
Merge develop to main
Tag release version
Deploy to production
Verify health check
Update Jira status
🤖 AI Tasks (Claude)
Create release PR
Generate release notes
Create git tag
Update Jira to Done
Notify stakeholders
Output: Feature live in production

## Slide 16
Stage 8: MONITOR
OWNER: All
Post-deployment monitoring. Catch issues early.
Key Points
Check logs for errors
Monitor performance
User feedback tracking
Rollback if needed
Post-incident review
🤖 AI Tasks (Claude)
Check GCP logs for errors
Analyze error patterns
Diagnose reported issues
Suggest fixes
Initiate rollback if needed
Output: Healthy production system or documented incident

## Slide 17
Sprint Operations
Sprint Cadence
1-week sprints (Mon-Fri)
Planning: Friday 2 PM
Standup: Daily sync
Retro: Every other Friday
Communication
#helm-dev for development
#helm-deploys for releases
Direct DM for urgent
All decisions documented
Meetings
Product Planning: Mon/Wed
Sprint Planning: Fri 2 PM
Retro: Alt Fridays
No other required meetings
Key: Minimize meetings. Maximize async communication. Document everything.

## Slide 18
Backlog Management
Backlog MCP (AI-Native)
Claude can read/write tasks
Integrated with development
Automatic status updates
Sprint-aware task management
Jira (External Tracking)
All tickets use MIN project
Links to Backlog tasks
Stakeholder visibility
Time tracking
Priority Levels
P0 (Critical): Production down, security issue - Drop everything
P1 (High): Blocking user work - This sprint
P2 (Medium): Important feature - Next sprint
P3 (Low): Nice to have - Backlog

## Slide 19
Definition of Ready (DoR)
CHECKLIST
☐ Jira ticket exists with clear title
☐ Acceptance criteria documented
☐ Technical spec written and approved
☐ Dependencies identified
☐ Effort estimated (story points)
☐ Priority assigned
☐ Assigned to developer
☐ No blockers identified
Task cannot enter sprint unless ALL items are checked. No exceptions.

## Slide 20
Definition of Done (DoD)
CHECKLIST
☐ Code complete and committed
☐ Tests written and passing
☐ PR created with template
☐ Code review approved
☐ CI pipeline passes
☐ Deployed to staging
☐ QA testing passed
☐ Jira updated to Done
Task is not Done until ALL items are checked. "Working on my machine" is not Done.

## Slide 21
Communication Channels
#helm-dev
Development discussion
Questions, decisions, updates
#helm-deploys
Deployment notifications
Auto-posted by CI/CD
Direct DM
Urgent issues
Blockers, P0 incidents
Jira Comments
Ticket discussion
Requirements, clarifications
Default to async. If it can wait until tomorrow, write it in Slack. DMs for urgent only.

## Slide 22
Meeting Formats
Meeting
Frequency
Duration
Attendees
Purpose
Product Planning
Mon/Wed
1 hour
Bill + Dom
Prioritize backlog, discuss features
Sprint Planning
Friday Afternoon
1 hour
Dom + Charles
Commit to sprint work
Retrospective
Alt Fridays
30 min
All
Improve process
Daily Standup
Daily sync
15 min
All
Resolve Blocks
No other recurring meetings. Ad-hoc only when absolutely necessary.

## Slide 23
Git Practices
Branch Strategy
main: Production code
develop: Integration branch
feature/*: New features
fix/*: Bug fixes
Commit Messages
Format: type(scope): description
Include Jira ticket: [MIN-XXX]
Types: feat, fix, docs, refactor
Descriptive but concise
PR Requirements
Use PR template
Link to Jira ticket
Tests must pass
At least one approval required

## Slide 24
Claude Configuration
CLAUDE.md File
Project-specific instructions
Code patterns to follow
Testing requirements
Commit message format
File naming conventions
Architecture guidelines
AI Best Practices
"Process" not "prompt and pray"
Always verify AI output
Keep context focused
Use clear, specific prompts
Review generated tests
Check for security issues

## Slide 25
QA Process
1
Automated Tests
CI runs all tests on PR
→
2
Code Review
Dom reviews all PRs
→
3
Staging Deploy
Auto-deploy on merge
→
4
Manual QA
Test acceptance criteria
→
5
Sign-off
QA approves for prod
Open Question: Who owns QA? Needs to be assigned before go-live.

## Slide 26
Success Criteria
Sprint Completion
> 80% of committed work done
Story points completed / committed
Cycle Time
< 5 days from ready to done
Average task completion time
Deployment Frequency
> 2 deploys per week
Production deployments
Bug Rate
< 1 P0/P1 per sprint
Critical bugs introduced

## Slide 27
Risks & Mitigations
⚠ Offshore timezone gaps
✓ Clear async communication, documented decisions
⚠ AI code quality
✓ Mandatory code review, test requirements
⚠ Scope creep mid-sprint
✓ Sacred sprint commitment, P0-only exceptions
⚠ Single point of failure (Dom)
✓ Document everything, cross-train team

## Slide 28
Nice-to-Have (Future)
PHASE 2
○ Feature flags for gradual rollouts
○ Automated performance testing
○ A/B testing infrastructure
○ Advanced monitoring dashboards
○ Automated dependency updates
○ Chaos engineering
These are NOT required for go-live. Consider for future sprints based on team bandwidth.

## Slide 29
Non-Functional Requirements
Performance
API response < 2s
Page load < 3s
Support 100 concurrent users
Availability
99% uptime target
Graceful degradation
Auto-restart on failure
Security
No secrets in code
HTTPS only
Input validation

## Slide 30
Appendix: Runbook Templates
APPENDIX
Deploy to Production
Template created
docs/runbooks/deploy.md
Rollback Procedure
Template created
docs/runbooks/rollback.md
Incident Response
Template created
docs/runbooks/incident.md
On-call Rotation
To be defined
docs/runbooks/oncall.md

## Slide 31
Appendix: Incident Severity
APPENDIX
Severity
Response Time
Examples
P0 - Critical
Immediate
Production down, security breach, data loss
P1 - High
< 1 hour
Major feature broken, blocking users
P2 - Medium
< 4 hours
Feature degraded, workaround exists
P3 - Low
Next sprint
Minor bug, cosmetic issue